## Projects
Title | Trello | Details | Link | Team | Lead | Status | Modified | Scope | Project Health | % Complete | Sem Complete | Sponsor* | Start Date* | End Date* | Duration | Planned Total Hrs* | DB | CH | JH | AB | CO | SW | EH | Up Next Priority | Online Learning | CurrDev | PW | Campus | Other | Org Impact Score | *Learning Model (Daniel) | *Program Eval (Curtis) | *Measuring T&L (Steve) | *Quality Instruction (Josh) | *Quality Course Design (Ben) | Reduce Cost | Student Experience | Tools | Other2 | Initiatives Impact Score | R&D: Safe | R&D: Big Bet | Evaluation
3rd Semester Survey Consolidation | Y | View | https://trello.com/c/WDTL0LFx | RED | Curtis | In Progress |  | Medium | Green | 85 |  | Bryan J | 2017-05-01 | 2017-08-01 | 92 | 0 | [13 empty] | 0 | [9 empty] | 0
Academic Start Student Feedback Evaluation Strategy | Y | View | https://trello.com/c/G4ititkg/365-lesson-level-evaluation-strategy | RED |  | Archived |  | Medium |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | 13 | 0 | 0 | 2
Activity-level Feedback: Product Develoment | Y | View | https://trello.com/c/jeBSR1uo | RED | Steve S | Up Next |  | Small |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 4 | 1 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 0 | 6 | 1 | 0 | 3
Analysis of Cheating | Y | View | https://trello.com/c/9eqz5dpI | RED | Steve S | In Progress |  | Small |  |  |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 3 | 1 | 2 | 2 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 6 | 0 | 0 | 3
Assist Online Instruction with Survey Practices | Y | View | https://trello.com/c/xjKYsFO4 | RED |  |  |  | Small |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 50 |  | 20 |  | 30 |  |  |  | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 3 | 0 | 7 | 0 | 0 | 2
Bio 264/265 Pass-rate Evaluation | Y | View | https://trello.com/c/Gt9YvnwT | RED | Daniel | Complete |  | Medium | Green | 100 | WI17 | Ben | 2016-11-01 | 2017-05-01 | 181 | 50 | 50 | [7 empty] | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 1 | 0 | 0 | 8 | 0 | 0 | 2
BYUI LMS Grades added to the DW |  |  |  | Data | Aaron | In Progress |  |  |  | 80 |  | Ben | 2017-02-01 | 2017-05-01 | 89 | 50 |  |  |  | 50 |  |  |  |  | 3 | 3 | 3 | 3 | 0 | 0 | [9 empty] | 0
BYUI LMS Instructor Usage added to the DW |  |  |  | Data | Aaron | In Progress | [6 empty] | 2018-01-01 | 2018-02-01 | 31 | 0 | [8 empty] | 5 | 1 | 1 | 1 | 0 | 0 | [9 empty] | 0
CCDP - I-Learn Gradebook sub-report | Y | View | https://trello.com/c/U9DLL8SA | RED | Joshua | In Progress |  | Medium | Yellow | 65 |  | Ben | 2017-03-01 | 2017-08-01 | 153 | 0 | [8 empty] | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 9 | 0 | 1 | 0
Competency-based Education | Y | View | https://trello.com/c/ranTTWUZ | RED | Joshua | Complete |  | Small |  | 100 | S17 | Ben | 2017-01-01 | 2017-07-01 | 181 | 0 | [8 empty] | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 6 | 0 | 0 | 2
Live Course Review Strategy | Y | View | https://trello.com/c/RzXPQOoq | RED | Daniel | Complete |  | Small | Green | 100 | WI17 | Ben | 2016-09-01 | 2016-12-01 | 91 | 40 | 40 | [7 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 1 | 5 | 0 | 12
Consultation with Instruction | N |  |  | RED | Joshua | [6 empty] | Joel | 2018-01-01 | 2018-02-01 | 31 | 0 | [13 empty] | 0 | [9 empty] | 0
Course Council Data portal - Initial Release | Y | View | https://trello.com/c/BBuBf51r | RED | Joshua | Complete |  | Large |  | 100 | F16 | Ben | 2016-05-01 | 2016-10-01 | 153 | 70 |  |  | 10 | 60 |  |  |  |  | 3 | 4 | 2 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 0 | 2 | 4 | 0 | 15 | 0 | 3 | 0
Course Council Health Evaluation | Y | View | https://trello.com/c/aTj6khYa | RED | Curtis | Complete |  |  |  | 100 |  | Ben | 2016-10-01 | 2017-01-01 | 92 | 30 |  | 30 | [11 empty] | 0 | [9 empty] | 0
Course Health Flags | Y | View | https://trello.com/c/6MkQ0jVC | RED |  |  |  | Small |  |  |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 2 | 1 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 2 | 5 | 0 | 12 | 0 | 0 | 2
Data Validation & Exploration | Y | View | https://trello.com/c/ZZdlUpaM | RED | Curtis | Complete |  |  |  | 100 |  | Ben | 2016-10-01 | 2016-12-01 | 61 | 50 | 20 | 30 | [6 empty] | 3 | 3 | 3 | 1 | 0 | 0 | [9 empty] | 0
Diagnostic Assessment Proof of Concept | Y | View | https://trello.com/c/D8j3kC3q | RED | Steve S | Up Next |  | Large |  | 0 |  | Ben | 2017-08-01 | 2018-06-01 | 304 | 0 | [7 empty] | 2 | 3 | 3 | 3 | 1 | 0 | 10 | 0 | 3 | 4 | 3 | 3 | 0 | 2 | 2 | 0 | 17 | 1 | 3 | 1
Due Dates | Y | View | https://trello.com/c/0Rl2oUNo | RED |  |  |  | Medium |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 2 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 7 | 0 | 0 | 3
EnglishConnect 3 POC I | Y | View | https://trello.com/c/XUCf77ac | RED | Curtis | Complete |  | Large | Green | 100 | S17 | Eric | 2017-01-01 | 2017-07-01 | 181 | 100 |  | 100 | [6 empty] | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 3 | 5
EnglishConnect 3 POC II | Y | View | https://trello.com/c/sDdAuiPu | RED | Curtis | In Progress |  | Medium |  |  |  | Eric | 2017-08-01 | 2018-01-01 | 153 | 0 | [7 empty] | 1 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 3 | 5
Qualtrics End-of-Course Evaluation Data Definitions | Y |  | https://tasks.office.com/webmailbyui.onmicrosoft.com/EN-US/Home/Task/tjp-XIeQxE2Ll-eWBJ5EbGQADL6U | Data | Daniel | Complete |  | Small | Green | 100 | S17 | Ben | 2017-06-01 | 2017-07-01 | 30 | 0 | [8 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0
Improve Transcript Process |  |  |  | P&C | Steve W | In Progress |  |  |  | 30 |  |  | 2018-01-01 | 2018-02-01 | 31 | 30 | [5 empty] | 30 | [7 empty] | 0 | [9 empty] | 0
Instructional Teams | Y | View | https://trello.com/c/0RSVUHUv | RED | Steve S | Up Next |  | Large |  | 0 |  | Joel | 2017-08-01 | 2018-04-01 | 243 | 0 | [7 empty] | 1 | 5 | 1 | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 5 | 1 | 3 | 2 | 0 | 0 | 14 | 0 | 4 | 4
Instructor growth - measure, incentivize and report | Y | View | https://trello.com/c/8bci8L2b | RED | Joshua | Up Next |  | Large |  |  |  | Joel | 2017-07-01 | 2017-10-01 | 92 | 0 | [7 empty] | 1 | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | x | x | x
Instructor Pre-Hiring and Performance Correlation | Y | View | https://trello.com/c/AVOalSuP | RED | Daniel | Complete |  | Micro | Green | 100 | Su17 |  | 2017-07-01 | 2017-08-01 | 31 | 10 | 10 | [7 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 1
Instructor to Student Feedback | Y | View | https://trello.com/c/lWe6R1j3/397-instructor-feedback-touchpoints-project | RED | Joshua | Up Next |  | Medium |  | 0 |  | Joel | 2018-01-01 | 2018-02-01 | 31 | 100 |  | 100 | [5 empty] | 2 | 5 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 4 | 0 | 0 | 10 | 4 | 1 | 1
Learning Model Measurement | Y | View | https://trello.com/c/YavEHr1V | RED | Curtis | Up Next |  | Large |  |  |  | Peter | 2017-07-01 | 2018-01-01 | 184 | 0 | [7 empty] | 1 | 4 | 4 | 2 | 1 | 0 | 0 | 5 | 0 | 0 | 4 | 4 | 0 | 2 | 0 | 0 | 15 | 1 | 0 | 4
Pathway Sites Data Definitions | Y |  | https://tasks.office.com/webmailbyui.onmicrosoft.com/EN-US/Home/Task/MxGa4ichrE2Zx6vaZAbqZGQAHm_G | Data | Daniel | In Progress |  | Small | Green | 50 |  | Ben | 2017-07-01 | 2017-08-01 | 31 | 0 | [8 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0
Mentoring Technology Solution | Y | View | https://trello.com/c/2LnzHN1V/569-mentoring-technology-solution | RED | Joshua | Archived |  | Small |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 1 | 0 | 0 | 5 | 1 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 2 | 1
OCR-M Added to the Data Warehouse |  |  |  | Data | Aaron | In Progress |  |  |  | 0 |  | Joel | 2018-01-01 | 2018-02-01 | 31 | 0 | [8 empty] | 4 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Online Student Grievance Process | Y | View | https://trello.com/c/Tr3zh7Td | RED | Curtis | Complete |  |  |  | 100 |  | Lynne | 2016-10-01 | 2016-12-01 | 61 | 30 |  | 30 | [20 empty] | 0 | 0
Outcomes and Assessment Improvement | Y | View | https://trello.com/c/aSRz088i | RED | Curtis | On Hold |  | Medium | Red | 50 |  | Ben | 2018-01-01 | 2018-02-01 | 31 | 0 | [8 empty] | 3 | 4 | 3 | 2 | 0 | 0 | [9 empty] | 0
Pathway Effect | Y | View | https://trello.com/c/s3l7NzTc | RED | Curtis | Complete |  | Small |  | 100 |  | Ben | 2016-10-01 | 2016-12-01 | 61 | 0 | [8 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0 | 0 | 2
Video Content in Online Courses | Y | View | https://trello.com/c/93VNZXbD | RED | Daniel | In Progress |  | Medium | Green | 95 |  |  | 2016-12-01 | 2017-08-01 | 243 | 30 | 30 | [7 empty] | 1 | 3 | 2 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 2
PathwayConnect Curriculum Evaluation | Y | View | https://trello.com/c/0r2y4TpY | RED | Curtis | Up Next |  | Medium |  |  |  | James F | 2017-08-01 | 2018-03-01 | 212 | 0 | [7 empty] | 1 | 1 | 2 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 4 | 0 | 1 | 0 | 0 | 13 |  |  | 5
PathwayConnect Evaluation Strategy | Y | View | https://trello.com/c/bLrzcrGM | RED | Curtis | In Progress |  | Large |  | 1 |  | Bryan J | 2017-08-01 | 2018-03-01 | 212 | 0 | [8 empty] | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 5 | 2 | 1 | 1 | 2 | 3 | 3 | 0 | 17 | 0 | 0 | 5
Perusall R&D | Y | View | https://trello.com/c/oMRtN8kM | RED |  |  |  | Small |  |  |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 0 | 3
Product Development: Pilot Evaluation | Y | View | https://trello.com/c/iHigzfXE | RED | Curtis | Complete |  |  |  | 100 |  | Ben | 2017-02-01 | 2017-05-01 | 89 | 80 |  | 80 | [11 empty] | 0 | [9 empty] | 0
I-Learn 3.0 Usability Task Force | Y | View | https://trello.com/c/8DR4SHRw | RED | Daniel | Archived |  | Medium | Yellow | 40 |  | Carry | 2018-01-01 | 2018-02-01 | 31 | 0 | [13 empty] | 0 | [9 empty] | 0
Redeveloment and Improvement Project Analysis | Y | View | https://trello.com/c/wXv61poI | RED | Steve S | Up Next |  | Small |  | 0 |  | Peter | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 1 | 1 | 5 | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 0 | 6 | 0 | 0 | 3
Refine Instructor Survey | Y | View | https://trello.com/c/qsAXGe0n | RED | Joshua | Up Next |  | Small |  |  |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 3 | 0 | 7 | 0 | 0 | 3
Remote Proctoring Evaluation | Y | View | https://trello.com/c/7dPAzcQt | RED | Joshua | Complete |  | Medium | Green | 100 | S17 | Ben | 2017-01-01 | 2017-07-01 | 181 | 80 |  |  | 80 | [5 empty] | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 3 | 3 | 2 | 14 | 0 | 1 | 3
Split TGL into Mentor and Evaluator | Y | View | https://trello.com/c/fyrbXXYC | RED | Joshua | Up Next |  | Large |  |  |  | Joel | 2017-07-01 | 2017-10-01 | 92 | 0 | [7 empty] | 1 | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | x | x | x
Strategies for Measuring Learning | Y | View | https://trello.com/c/H6bLf8D7 | RED |  |  |  | Medium |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 100 |  |  | 100 |  |  |  |  | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 3 | 3 | 0 | 1 | 1 | 0 | 14 | 2 | 2 | 3
Discussion Board Rubric Development | Y | View | https://trello.com/c/38vk04bn | RED | Daniel | In Progress |  | Medium |  |  |  | Peter | 2017-08-01 | 2018-04-01 | 243 | 0 | [8 empty] | 1 | 4 | 1 | 1 | 0 | 0 | 4 | 0 | 0 | 1 | 4 | 0 | 3 | 0 | 0 | 12 | 2 | 0 | 2
Student milestones added to the DW |  |  |  | Data | Aaron | In Progress |  |  |  | 80 |  |  | 2017-02-01 | 2017-05-01 | 89 | 40 |  |  |  | 40 |  |  |  |  | 3 | 2 | 5 | 4 | 0 | 0 | [9 empty] | 0
Student Community, TOA | Y | View | https://trello.com/c/3yXgBzOH | RED | Daniel | Up Next |  | Large |  | 0 |  |  | 2017-08-01 | 2017-11-01 | 92 | 50 |  |  | 50 |  |  |  |  | 1 | 3 | 3 | 3 | 1 | 0 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 5 | 0 | 0 | 13 | 2 | 5 | 1
Student Ownership | Y | View | https://trello.com/c/nWdbRrPU | RED | Daniel | Up Next |  | Large |  | 0 |  |  | 2017-07-01 | 2018-05-01 | 304 | 70 | 70 | [6 empty] | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 10 | 4 | 1 | 1
Survey Policy Evaluation | Y | View | https://trello.com/c/Z4V4P7kJ | RED | Curtis | Complete |  | Small | Green | 100 | WI17 | Ben | 2016-04-01 | 2016-07-01 | 91 | 30 |  | 30 | [11 empty] | 0 | [9 empty] | 0
Synchronous/Asynchronous Preference and Personality | Y | View | https://trello.com/c/N2V8NKxt | RED | Joshua | Complete |  | Small | Green | 100 | WI17 | Ben | 2016-09-01 | 2017-02-01 | 153 | 0 | [13 empty] | 0 | [9 empty] | 0
Teaching Assistants Round 2 | Y | View | https://trello.com/c/3cZIp2Lb | RED | Joshua | Complete |  | Small |  | 100 | F15 |  | 2015-01-01 | 2017-07-01 | 912 | 30 |  |  | 30 | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 3 | 2 | 0 | 0 | 10 | 3
Understand Online Program Attrition | Y | View | https://trello.com/c/2ZL1ZHTp | RED |  |  |  | Large |  |  |  |  | 2017-07-15 | 2017-10-15 | 92 | 0 | [7 empty] | 1 | 2 | 3 | 4 | 2 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 4 | 3 | 3 | 0 | 16 | 0 | 0 | 4
Student Profiles: Product Development | Y | View | https://trello.com/c/d2XVbcBP/308-product-development-student-profiles-attributes-medium | RED | Daniel | Up Next |  | Large |  | 0 |  | Ben | 2017-07-01 | 2017-10-01 | 92 | 50 |  | 30 |  | 20 |  |  |  | 1 | 1 | 3 | 3 | 2 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 0 | 3 | 0 | 0 | 11 | 0 | 0 | 5
Walk-in Service: Product Develoment | Y | View | https://trello.com/c/H50hw62u | RED | Joshua | Up Next |  | Small |  | 0 |  |  | 2018-01-01 | 2018-02-01 | 31 | 0 | [7 empty] | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 8 | 1 | 1 | 3
Watch List: Product Development | Y | View | https://trello.com/c/6vo5lBWk | P&C | Steve W | Up Next |  | Micro |  | 0 |  |  | 2017-07-01 | 2017-07-15 | 14 | 0 | [7 empty] | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 5 | 0 | 0 | 2
Learning Model Research Agenda Development | Y | View | https://trello.com/c/9Aw2eqVO | RED | Daniel | In Progress |  | Small | Green | 40 |  | Ben | 2017-08-01 |  | #NUM! | 0 | [7 empty] | 1 | 3 | 3 | 2 | 0 | 0 | 0 | 5 | 0 | 2 | 2 | 4 | 0 | 3 | 0 | 0 | 16 | 0 | 0 | 3
Formulas:
Duration = DATEDIF(Table1[[#This Row],[Start Date*]],Table1[[#This Row],[End Date*]],"d")

## Products
Title | Description | Team | Previous Owner (to be deleted) | Owner | Load | PSD Status | Last Reviewed | Notes
Online Executive Reports Index | List of high-level reports for online administrators. | Course Improvement | Ben | David | 1 | Complete | 2017-03-08
External Research Coordination | Coordinating and maintaining relationships with external researchers to serve research and evaluation needs in Online Learning. | RED | Curtis | Curtis | 1 | Incomplete
Course Outcome Achievement Reporting | Reporting of students' course outcome achievement to course councils. | RED | Curtis | Curtis | 1 | Incomplete
Course Council Health Report | Report to identify effective and unhealthy course councils. | RED | Curtis | Curtis | 1 | Complete
State of the Portfolio | High-level report of the performance of Online Learning. | RED | Curtis | Curtis | 1 | Incomplete
Student Team | Management of student employees to help serve research and evaluation needs in Online Learning. | RED | ? | Daniel | 3 | Incomplete
Live Course Review | Course-specific review of selected BYU-Idaho Online courses. | RED | Daniel | Daniel | 3 | Complete | 2017-07-31 | 2018-07-31
End-of-Course and Mid-Course (Surveys) | Course and Instructor evaluation surveys | RED | Daniel | Daniel | 1 | Incomplete
Lesson Level Feedback (Survey) | Weekly student course feedback data | RED | Daniel | Daniel | 1 | Incomplete
Instructor Feedback (Survey) | Instructor feedback on course performance and teaching experience. | RED | ? | Joshua | 1 | Incomplete |  | Owner: Daniel or Curtis
Walk-in Service | Record and manage requests for info that will take less than 4 hours of time. | RED | ? | Joshua | 1 | Complete | 2017-03-27
Online Student and Instructor Survey Log | Log of the surveys sent to online students and instructors. | RED | Curtis | Joshua | 1 | Complete
Course Council Data Portal | Course-specific data for online course council members and administrators. | RED | Joshua | Joshua | 1 | Complete
Pilot Evaluations | Various levels of reporting for course councils and administrators to understand the pilot semester performance. | RED | Curtis | New Person | 1 | Complete
Lessons Learned | A list of lessons learned from reports with meta-data attached for searchability. | RED | Curtis | New Person | 2 | Incomplete
Sub-4 Report | Current and historical lists of courses whose overall average is below 4. | RED | Daniel | Daniel | 1 | Incomplete
Course Council Support (Role of the P&C Man.) | Describes the role of the P&C Manager relative to the roles of other groups | P&C |  | Steve W. | 3 | Incomplete |  | Steve working on this now and then we'll get feedback from others (4/21/17)
Course Statistics by Semester | Shows key indicators of a course. Can be rolled up in a variety of ways. | Data |  | Aaron | 1
Learning Model Initiative | Research and evaluation agenda related to the learning model. | RED |  | Daniel |  | Incomplete
Program Evaluation Initiative | Develop and implement patterns for program evaluation | RED |  | Curtis |  | Incomplete |  | Currently applies only to Academic Start and ECI. May also include online academic programs.
Measuring Teaching and Learning Initiative | Ensure we have valid and reliable methods | RED |  | Stokes |  | Incomplete
Quality Instruction Initiative | Evaluation and R&D planning related to quality instruction | RED |  | Joshua |  | Incomplete
Quality Course Design | Evaluation and R&D related to quality course design | RED |  | Ben |  | Incomplete
Knowledgebase | A place to manage and share knowledge. | P&C |  | Emily | 3 | Incomplete

## DropDowns
Area | Department | Sponsor | Team | Steward | Status | Scope | Health | Month | Year | Client Breakdown |  | Employee Breakdown |  | Impact Value
Pathway | Instruction | Alan | RED | Daniel | Up Next | Micro | Green | Jan | 2013 | Online Learning | #REF! | Christy Owens | 0 | Jumbo
Student Services | Online CurrDev | Eric | Data | Curtis | On Hold | Small | Yellow | Feb | 2014 | Curriculum Development | #REF! | Emily Herman | 0 | High
Curriculum Development | Campus CurrDev | Peter | Review | Joshua | In Progress | Medium | Red | Mar | 2015 | Pathway | #REF! | Aaron Ball | 0 | Medium
Online Learning | Course Improvement | Ben | P&C | Aaron | Complete | Large |  | Apr | 2016 | Campus | #REF! | Joshual Holt | 0 | Low
Online-wide | Employment and Sched | Matt |  | Steve W | Archived | Jumbo |  | May | 2017 | Other | #REF! | Steve Willis | 0 | None
Online Programs | Multiple | Joel |  | Emily |  |  |  | Jun | 2018 |  |  | Daniel Balls | 0
Executive Office |  | Rob |  | Christy |  |  |  | Jul |  |  |  | Curtis Henrie | 0
University-wide |  | Carry |  | Steve S |  |  |  | Aug
Other |  | JD | [5 empty] | Sep
|  | Lynne | [5 empty] | Oct
|  | Bryan J | [5 empty] | Nov
|  | James F | [5 empty] | Dec